## LogFrame
REGINALD MOFOKENG
IMPACT |  | Learner transport access to all learners in country
Indicator
Frequency
Source of data
OUTCOME |  | Access to Learner Transport to scholars |  | Learners arriving on time
Indicator
Frequency
Source of data
Final Output |  | Reduced abseeitism
Indicator
Frequency
Source of data
Intermediate outputs |  | Approved policy for learner transport
Activities |  |  |  |  | ACT 3.7 | Monitor and implement the implentation plan
Indicator
Frequency | [5 empty] | Quarqqqqqqqqtely
Source of data |  | Stats Sa
Activities |  |  |  |  | ACT 3.7 | Pay subsidized learner transport operators
Indicator
Frequency | [5 empty] | qqq
Source of data
Activities |  |  |  |  | ACT 3.6 | Contract Learner transport operators,
Indicator
Frequency
Source of data
Activities |  |  | ACT 2.5 | Approve the Provincial implementation plan | ACT 3.5 | Verify and review invoices from subsidized learner transport opertors
Indicator
Frequency
Source of data
Activities | ACT 1.4 | Approve National Policy | ACT 2.4 | Incorporate the cost of the learner transport plan | ACT 3.4 | contact learner transport operators
Indicator
Frequency
Source of data
Activities | ACT1,3 | Consult On Nationa Draft Policy | ACT 2.3 | Estimate the cost of the the implementation plan for learner transport plan | ACT3.3 | Screen and select learner transport operators
Indicator
Frequency
Source of data
Activities | ACT 1.2 | Develop A draft a National Policy | ACT 2.2 | Engage stake holders on the Provincial learner transport implementation plan | ACT 3.2 | Issue a call for proposals for learner transport services
Indicator
Frequency
Source of data
Activities | ACT 1.1 | Conduct a National review of the demand of learner transport | 2.1 | Draft the Provincial learner transport implementation plan | ACT 3.1 | Dissiminate information on the route description
Indicator |  | No of learners that need Learner Transport
Frequency |  | Daily
Inputs |  | Director of the Programme, Managers |  |  |  | SCM officials,Contractors
Performance indicator | [5 empty] | SCM officials,Contractors
Frequency
Programme elements |  | Develop policy framework |  | Provincial Lerner Transport implemtation plan |  | Contracted operators
Responsibility |  | Policy and Monitoring and evaluation |  | Policy and Planning |  | Administration