## 0. Start here
Are we building schools or funding contractors PER on the performance of Building of Schools
Pauli Visagie
Free State Treasury
DATE: 1-5 July & 7-12 July 2019
Version No:

## 1. Table of Contents
Table of Contents | 1
Logical Framework - Example | 2
Logical Framework - Building of schools | 3

## Sheet6 (hidden)
Intermediate Outcome
Final output
Intermediate outputs
Activities
Immediate Outcome
Final outcome
Inputs

## 2. Logical framework_Example
IMPACT | IMP1 | Healthier learners
Indicator |  | Learner attendance rate
Frequency |  | Annual
Source of data |  | Education Management Information Systems
OUTCOME | OUTC1 | Fewer accidents and assaults in toilets | OUTC2 | Access to functional ablution facilities
Indicator |  | Number of accidents and assaults |  | Ratio of learners to toilets
Frequency |  | Annual |  | Annual
Source of data |  | Education Management Information Systems |  | Survey
Final Output | FOUT1 | Safe toilets | FOUT2 | Clean and functioning toilets | FOUT3 | Awareness of good hygiene practice
Indicator |  | % of schools with no or dilapidated toilet infrastructure |  | % of schools with clean and functioning toilets |  | % of learners who understand why hand hygiene is important.
Frequency |  | Bi-annual |  | Bi-annual |  | Bi-annual
Source of data |  | School inspections |  | School inspections |  | Post training evaluation (training providers)
Intermediate outputs | IOUT1 | Approved policy on School Sanitation | IOUT2 | Built, renovated and repaired toilets | IOUT# | Trained learners
Indicator |  | Policy published in government gazette |  | Number of new toilets built, number of toilets renovated and repaired |  | Number of learners trained
Frequency |  | DBE |  | PEDs |  | PEDs
Source of data |  | DBE website |  | Districts |  | Districts
Activities | ACT 1.4 | Prepare policy on School Sanitation | ACT 2.4 | Maintain the toilets in good working order | ACT 3.2 | Train tlearners on personal hygiene
Indicator |  | Policy approved by DG |  | % spend on school maintenance per district |  | Number of training programmes delivered per district
Frequency |  |  |  | Annual |  | Monthly
Source of data |  |  |  | BAS |  | Districts
Activities | ACT 1.3 | Cost the interventions and determine funding | ACT 2.3 | Monitor progress against the implementation plan | ACT 3.1 | Develop curriculum for training programme
Indicator |  | Costed implementation plan |  | Unit cost of each new toilet built, unit cost of each toilet renovated |  | Approved training programme
Frequency |  |  |  | Quarterly |  | As needed
Source of data |  |  |  | BAS
Activities | ACT 1.2 | Identify the sanitation interventions | ACT 2.2 | Roll out the implementation plan
Indicator |  |  |  | Actual versus budgeted expenditure
Frequency |  |  |  | Quarterly
Source of data |  |  |  | BAS
Activities | ACT 1.1 | Develop the problem statement | ACT 2.1 | Develop a costed implementation plan |  | Monitor progress against the implementation plan
Indicator |  |  |  | Approved provincial costed implementation plan and budget |  | Unit cost of each new toilet built, unit cost of each toilet renovated
Frequency |  |  |  | As needed |  | Quarterly
Inputs |  | District circult manager, school principal, school teachers |  | Materials, building contractors, circuit manager, school principal |  | BAS
Performance indicator |  |  |  | SCM officials, contractors, building material |  | Training material, trainers
Frequency
Programme elements |  | Develop policy framework |  | Construct, repair and rehabilitate toilets |  | Train learners
Responsibility |  | Policy Unit |  | CD: Infrastructure Management |  | CD: Capacity building

## 2. Logical framework Schools
IMPACT |  | Educatied Learners
Indicator |  | Learner attendance rate
Frequency |  | Annual
Source of data |  | Education Management Information Systems (EMIS)
OUTCOME |  |  |  | Access to functional schools
Indicator
Frequency
Source of data
Final Output |  |  | FOUT2 | Functioning Schools | FOUT2 | Functioning Schools
Indicator |  |  |  | Nr of completed functioning schools |  | Nr of completed functioning schools
Frequency |  |  |  | Bi-annual |  | Bi-annual
Source of data |  |  |  | School inspections |  | School inspections
Intermediate outputs |  |  | IOUT2 | Built Schools | IOUT3 | Draft report
Indicator |  |  |  | Number of schools built
Frequency |  |  |  | Bi-annual
Source of data |  |  |  | School inspections
|  |  | ACT 2.6 | Monitor SLA of contractors
Indicator |  |  |  | Progress in lign with SLA
Frequency |  |  |  | Quarterly
Source of data |  |  |  | SLA
|  |  | ACT 2.5 | Appoint contractors
Indicator |  |  |  | Nr of contractors appointed on time
Frequency |  |  |  | Once-off
Source of data |  |  |  | Provincial infrastrucrure Plan
Activities |  |  | ACT 2.4 | Call for proposals
Indicator |  |  |  | Nr of proposals received for each school
Frequency |  |  |  | Once-off
Source of data
Activities |  |  | ACT 2.3 | Draw Specifications for schools | ACT 3.2 | Comparative analysis between national norms & provincial cost
Indicator |  |  |  | Specification for each school |  | Nr of schools compared as per national norm | Note: Compare like with like, e.g. compare mega with mega, smart with smart
Frequency | [5 empty] | Annually
Source of data |  |  |  | Norms and Standard |  | Norms & Standards and IRM
Activities |  |  | ACT 2.2 | Draft Provincial infrastrucrure Plan | ACT 3.3 | Determine tender price of schools (in process and those finished from 2015/16 onwards)
Indicator |  |  |  | Approved provincial costed implementation plan and budget |  | Nr of tender prices identified
Frequency |  |  |  | Once-off
Source of data | [5 empty] | IRM
Activities | ACT 1.1 | National Infrastructure Policy on Schools | ACT 2.1 | Estimate of cost of schools Infrastructure Plan | ACT 3.1 | Review Performance of Infrastructure Plan
Indicator |  |  |  | Unit cost of each school to be built |  | Reporting of Performance of Infrastructure Plan
Frequency |  |  |  | Once-off |  | Quarterly
Source of data |  |  |  | Norms & Standard |  | IRM
Inputs |  | District circult manager, school principal, school teachers |  | Chief Director: Infrastructure Development, Materials, building contractors, circuit manager, school principal
Performance indicator |  |  |  | SCM officials, contractors, building material
Frequency
Programme elements |  | Develop policy framework |  | Infrastructure constructure
Responsibility |  | Director: Policy Development (Programme 2) |  | CD: Physical Resource Management