## Title
One Call' Service
Merge the Basic Accounting System and Logistical Information System oversight support units in the Northern Cape Provincial Treasury.
Can the same or beter results be achieved in a more effective and efficient way if the BAS and LOGIS units are merged?
Is there a need based on the current proposed structure to appoint more employees in the LOGIS unit?
Are there potential similarities/duplications between the two units?
2019-08-12
By
Shirene Maclean

## Introduction
PER to merge the BAS and LOGIS oversight units in the Northern Cape Provincial Treasury
This workbook contains expenditure analysis on the BAS and LOGIS units in the NC Provincial Treasury over the MTEF for 2016/2017 - 2018/2019 | Expenditure Analysis'!A1
This workbook contains projections on the cost for merging the units | Costing!A1
This workbook contains assumptions based on the information collected | Gen Assumptions'!A1
This workbook contains information regarding the resources/time needed to perform this KPA | Capacity Building'!A1
This workbook contains information regarding the resources/time needed to perform this KPA | Monitoring and Support'!A1
This workbook contains information on the general processes for BAS and LOGIS. It outlines the similarities and differences between the two units | Process flows'!A1
This workbook outlines the current approved structure for BAS and LOGIS, the proposed structure to be implemented, as well as the proposed structures based on the costing plan | Structure!A1

## Gen Assumptions
Assumptions
Financial Assumptions
[5 empty] | Salary Level 7 | Salary Level 9 | Salary Level 11
Salary notch 2018/2019 |  | 0 |  |  | 242475 | 356289 | 697011
Salary adjustment 2019/2020 |  | 522395.64 |  |  | 6.2% | 5.7% | 5.2%
Salary notch 20119/2020 |  | 514907.64 |  |  | 257508.45 | 376597.473 | 733255.572
PMDS 2017/2018 |  | 477080 | [5 empty] | 1.5%
Salary levels of key staff
Proposed structure |  |  |  | Scenario 1 - costed plan - based on 2019/2020 TCE |  |  | Scenario 2 - costed plan - based on 2019/2020 TCE
BAS Support and Administration | Salary Level |  | Salary Scale 2019/2020 | Salary level | BAS and LOGIS Management and Support | Full time TCE | Full time TCE
Deputy Director | 11 |  | 733255.572
Assistant Director | 10 |  | 522395.64
Assistant Director | 10 |  | 522395.64
Assistant Director | 10 |  | 522395.64
LOGIS Support and Management |  |  |  | Salary level | BAS and LOGIS Management and Support | Current Gross Salary | Current Gross Salary
Deputy Director | 11 |  | 733255.572 | 11 | Deputy Director | 733255.572 | 733255.572
Assistant Director | 10 |  | 514907.64 | 10 | Assistant Director | 522395.64 | 522395.64 |  | 522395.64
Assistant Director | 10 |  | 500276.64 | 10 | Assistant Director | 522395.64 | 0 |  | 514907.64
Assistant Director | 10 |  | 477081 | 10 | Assistant Director | 522395.64 | 522395.64 |  | 500276.64
Assistant Director | 9 |  | 376597.473 | 10 | Assistant Director | 514907.64 | 514907.64 |  | 477080
Financial Admin Officer | 8 |  | 357314.64 | 10 | Assistant Director | 500276.64 | 500276.64 |  | 0
Financial Admin Officer | 7 |  | 257508.45 | 10 | Assistant Director | 477081 | 477080
Financial Admin Officer | 7 |  | 257508.45 | 8 | Financial Administration Officer | 357314.64 | 357314.64
|  |  | 5774892.357 |  |  | 4150022.412 | 3627625.772
Projected savings based on costed plan |  |  | 1624869.945 |  |  |  | 2147266.585
[5 empty] | 28.14% |  | 37.18%
2 | 3 | 4 | 5
Total Cost to implement programme change
Setup costs |  |  |  | 693060
Training - LOGIS System Controller training for BAS System Controllers | Number of Officials to be trained | Duration of training (Days)
Accommodation | 3 | 10 | 1440 | 43200
Air transport | 3 | 10 | 6000 | 180000
Meals | 3 | 10 | 134 | 4020
Subsistence and Travel Allowance | 3 | 10 | 134 | 4020
Training - LOGIS train-the-trainer for BAS and LOGIS System Controllers |  |  |  | 0
Accommodation | 5 | 30 | 1440 | 216000
Air transport | 5 | 30 | 600 | 90000
Meals | 5 | 30 | 134 | 20100
Subsistence and Travel Allowance | 5 | 30 | 134 | 20100
Training - BAS training for LOGIS System Controllers |  |  |  | 0
Accommodation | 3 | 5 | 1440 | 21600
Air transport | 3 | 5 | 6000 | 90000
Meals | 3 | 5 | 134 | 2010
Subsistence and Travel Allowance | 3 | 5 | 134 | 2010
693060
General Assumptions |  |  |  | AD: System Controller - Scenario 1 | AD-Training Management and Support - scenario 1 | FAO - Scenario 1 | AD: System Controller - Scenario 2 | FAO - Scenario 2
Work days per annum | 252 |  | 252
Non core work days per annum | 10% |  | 25.2
Core work days per annum |  |  | 226.8
Work hours per annum | 8 |  | 1814.4 | 1814.4 | 1814.4 | 1814.4 | 1814.4 | 1814.4
Average work hours required for capacity building, monitoring and support |  |  |  | 1282.2 | 1238 | 931 | 1282.2 | 1486
Average work hours remaining for monitoring of suspense accounts, reporting, extra preparation time for training |  |  |  | 532.2 | 576.4 | 883.4 | 532.2 | 328.4
Average days remaining for monitoring of suspense accounts, reporting, extra preparation time for training |  |  |  | 66.525 | 72.05 | 110.425 | 66.525 | 41.05
Capacity Building |  |  | AD: System Controller - Scenario 1 | AD-Training Management and Support | FAO - Scenario 1 | FAO -Scenario 2 | AD: System Controller - Scenario 2
BAS Training |  |  | Hours required per FY to conduct training/attend forums | Hours required to manage/co-ordinate training sessions | Hours required for the administration of training sessions | Hours required to manage/co-ordinate training sessions and perform administrative functions | Hours required per FY to conduct training/attend forums
Number of sessions per FY (Provision made for 3 Adhoc sessions) | 10 |  | 576 | 344.5 | 260 | 500.5 | 576
LOGIS Training
Number of sessions per FY (Provision made for 1 Adhoc session) | 16 |  | 952 | 450.5 | 340 | 654.5 | 952
BAS Forums/Workshops
National (BAS and SCOA) | 8 |  | 64 | 64 | 64 | 64 | 64
Provincial | 4 |  | 20 | 20 | 20 | 20 | 20
LOGIS Forums
National | 4 |  | 48 | 48 | 48 | 48 | 48
Provincial | 4 |  | 20 | 20 | 20 | 20 | 20
Total input needed for Capacity building |  |  | 1680 | 947 | 752 | 1307 | 1680
Support Services |  |  | Average hours
Support Calls
Average hours spend by System controllers on BAS and LOGIS calls during the MTEF 2016/17-2018/2019 |  |  | 1659
Average hours spend by LOGIS Support (FAO's) on LOGIS calls during the MTEF 2016/17-2018/2019 |  |  | 291
Security Verifications (Currently still 12 Departments, will be 11 Departments once DENC and DALR&RD has fully merged | 12
BAS (4 Days per quarter - per department) |  |  | 1536
LOGIS (4 Days per quarter-per department) |  |  | 1536
Monitoring of suspense accounts and reporting |  |  | Current departments per System Controller | Proposed Departments per System Controller
BAS (1 AD will be responsible for 3 small departments) |  |  | 4 | 2/3
Monitoring of suspense accounts
Quarterly report on Department's activities
LOGIS (1 AD will be responsible for 3 small departments) |  |  | 6 | 2/3
Commitment and Accruals reports
Spend Analysis
Users
Current BAS users | 602
Number of users per System Controller | 200.6667
Current LOGIS users | 660
Number of users per System Controller | 330
Users with BAS and LOGIS user-ids (Needed to access both systems for officials who are responsible for payments and BAS functionalities) | 309
Average users per System Controller if the costed plan is approved | 190.6
Note on F17: SMaclean: Current Gross salary for permanent employees
Note on C88: SMaclean: Sec. Verifications is currently done within 2 to 3 days for BAS users

## Costing
Financial Assumptions
[6 empty] | Salary Level 7 | Salary Level 9 |  | Salary Level 11 |  | Level 1 to 7 |  | Level 8 to 10 |  | Level 11 to 12
|  | 0 | Salary notch 2018/2019 |  |  | 242475 | 356289 |  | 697011 |  | CPI + 1.0% |  | CPI + 0.5% |  | CPI
|  | 522395.64 | Salary adjustment 2019/2020 |  |  | 6.2% | 5.7% |  | 5.2% |  | 5.0% +1.0%
|  | 514907.64 | Salary notch 2019/2020 |  |  | 257508.45 | 376597.473 |  | 733255.572 |  | 6% |  | 5.5% |  | 5%
|  | 477080 | PMDS 2017/2018 | [6 empty] | 1.5%
|  | 500276.64 | [8 empty] | Growth Projections
Proposed structure |  |  |  |  | Scenario 1 - costed plan - based on 2019/2020 TCE |  |  |  | Scenario 2 - costed plan - based on 2019/2020 TCE |  | Current structure | Service Bonus | Proposed Structure | Service Bonus | Scenario 1 | Service Bonus | Scenario 2 | Service Bonus
BAS Support and Administration | Salary Level |  | Salary Scale 2019/2020 | Service Bonus | Salary level | BAS and LOGIS Management and Support | Full time TCE |  | Full time TCE |  | 2020/2021 |  | 2020/2021 |  | 2020/2021 |  | 2020/2021
Deputy Director | 11 |  | 733255.572 | [7 empty] | 769918.3506 |  | 769918.3506 |  | 0 |  | 0
Assistant Director | 10 |  | 522395.64 | 43532.97 | [6 empty] | 551127.4002 | 45927.2834 | 551127.4002 | 45927.2834 | 0 |  | 0
Assistant Director | 10 |  | 522395.64 | 43532.97 | [6 empty] | 551127.4002 | 45927.2834 | 551127.4002 | 45927.2834 | 0 |  | 0
Assistant Director | 10 |  | 522395.64 | 43532.97 | [6 empty] | 551127.4002 | 45927.2834 | 551127.4002 | 45927.2834 | 0 |  | 0
LOGIS Support and Management |  |  |  |  | Salary level | BAS and LOGIS Management and Support | Full time TCE | Service Bonus | Full time TCE | Service Bonus
Deputy Director | 11 |  | 733255.572 |  | 11 | Deputy Director | 733255.572 | 61104.631 | 733255.572 | 61104.631 | 769918.3506 |  | 769918.3506 |  | 769918.3506 |  | 769918.3506
Assistant Director | 10 |  | 514907.64 | 42908.97 | 10 | Assistant Director | 522395.64 | 43532.97 | 522395.64 | 43532.97 | 543227.5602 | 45268.9633 | 543227.5602 | 45268.9633 | 551127.4002 | 45927.2834 | 551127.4002 | 45927.2834
Assistant Director | 10 |  | 500276.64 | 41689.72 | 10 | Assistant Director | 522395.64 | 43532.97 | 522395.64 | 43532.97 | 527791.8552 | 43982.6546 | 527791.8552 | 43982.6546 | 551127.4002 | 45927.2834 | 551127.4002 | 45927.2834
Assistant Director | 10 |  | 477081 | 39756.75 | 10 | Assistant Director | 522395.64 | 43532.97 | 0 | 0 | 503320.455 | 41943.3712 | 503320.455 | 41943.3712 | 551127.4002 | 45927.2834 | 0 | 0
Assistant Director | 9 |  | 376597.473 | 31383.1227 | 10 | Assistant Director | 514907.64 | 42908.97 | 514907.64 | 42908.97 | 272958.957 | 22746.5798 | 397310.334 | 33109.1945 | 543227.5602 | 45268.9633 | 543227.5602 | 45268.9633
Administration Officer | 8 |  | 357314.64 | 29776.22 | 10 | Assistant Director | 500276.64 | 41689.72 | 500276.64 | 41689.72 | 376966.9452 | 31413.9121 | 376966.9452 | 31413.9121 | 527791.8552 | 43982.6546 | 527791.8552 | 43982.6546
Administration Officer | 7 |  | 257508.45 | 21459.0375 | 10 | Assistant Director | 477081 | 39756.75 | 477080 | 39756.6667 | 272958.957 | 22746.5798 | 272958.957 | 22746.5798 | 503320.455 | 41943.3712 | 503319.4 | 41943.2833
Administration Officer |  |  | 257508.45 | 21459.0375 | 8 | Financial Administration Officer | 357314.64 | 29776.22 | 357314.64 | 29776.22 | 272958.957 | 22746.5798 | 272958.957 | 22746.5798 | 376966.9452 | 31413.9121 | 376966.9452 | 31413.9121
Total Projected Expenditure |  |  | 5774892.357 | 359031.7677 |  |  | 4150022.412 | 345835.201 | 3627625.772 | 302302.1477 | 5963402.5884 | 368630.4906 | 6087753.9654 | 378993.1054 | 4374607.3668 | 300390.7514 | 3827145.1895 | 254463.3801
|  |  | 6133924.1248 |  |  |  | 4495857.613 |  | 3929927.9197 |  | 6332033.079 |  | 6466747.0708 |  | 4674998.1181 |  | 4081608.5695
[7 empty] | 1638066.5117 | 26.71% | 2203996.2051 | 35.93% |  |  | -134713.9918 | -2.127% | 1791748.9526 | 27.71% | 2385138.5012 | 36.88%
Expenditure | Salaries |  | Potential Savings (R'000) |  | Potential savings (%)
Proposed structure | 6466747.0708
Scenario 1 | 4674998.1181 |  | 1791748.9526 |  | 27.71%
Scenario 2 | 4081608.5695 |  | 2385138.5012 |  | 36.88%
Note on E17: SMaclean: Current Gross salary for permanent employees. Green indicate new and/or vacant posts to be filled. All vacancies will be filled on Salary Level 11, 10 and 7 respectively.

## Expenditure Analysis
Expenditure Analysis for the period 2015/2016 - 2018/2019
Row Labels | 2015/2016 | 2016/2017 | 2017/2018 | 2018/2019 | Grand Total
BAS Support | 2125164.87 | 2149398.96 | 2305267.68 | 2445651.9 | 9025483.41
Basic Salary | 1856190.65 | 1848458.91 | 2002679.7 | 2150202.72 | 7857531.98
Housing Allowances | 50808 | 48108 | 60060 | 56069.94 | 215045.94
NON PENSINABLE ALLOWANCES | 96258.72 | 104790.84 | 113609.28 | 121386.24 | 436045.08
PERFOMANCE BONUS | 0 | 0 |  |  | 0
SERV BASED |  | 18582 | 0 |  | 18582
SERVICE BONUS | 121907.5 | 100226.25 | 109155 | 117993 | 449281.75
LOGIS Support | 3023860.12 | 3264281.27 | 3540885.95 | 3186111.12 | 13015138.46
Basic Salary | 2657931.77 | 2884453.32 | 3134762.19 | 2836642.43 | 11513789.71
Housing Allowances | 74400 | 82800 | 96804 | 69795.92 | 323799.92
NON PENSONABLE ALLOWANCES | 84268.23 | 93835.17 | 103937.01 | 113310.72 | 395351.13
PERFOMANCE BONUS | 27183.12 | 18082.95 | 0 | 0 | 45266.07
SERV BASED | 0 | 0 |  |  | 0
SERVICE BONUS | 180077 | 185109.83 | 205382.75 | 166362.05 | 736931.63
Grand Total | 5149024.99 | 5413680.23 | 5846153.63 | 5631763.02 | 22040621.87

## Capacity Building
Current Scenario
| Unit | Employees | Trainers | Sessions scheduled per FY | Sessions scheduled per FY | Approximate input per trainer (hours)
| BAS | 1 Deputy Director, 3 Assistant Directors | 3 | 10 | Divided by 3 officials | 393.5
| LOGIS | 1 Deputy Director, 3 Assistant Directors, 4 Administration Officers | 1 | 16 | Conduct all training sessions | 1742.5
|  |  | - | - | - | -
| Scenario 1: 6 Assistant Directors (5 AD's to conduct training, 1 AD to coordinate training) and 1 Financial Administration Officer (to administrate training) | [7 empty] | Scenario 2: 5 Assistant Directors (5 AD's to conduct and coordinate training) and 1 Financial Administration Officer | [5 empty] | Approximate input needed for training preparation and finalisation
| 10 BAS Training sessions to be held per Financial Year as per the APP | [7 empty] | 10 BAS Training sessions to be held per Financial Year as per the APP | [5 empty] | Activity | Scenario 1 |  | Scenario 2
[16 empty] | FAO | AD | FAO
Approximate input needed to prepare, conduct and finalise training sessions. | BAS Training Sessions | Duration (Days) | Input(hours) needed to conduct training sessions | Approximate input(days) needed to prepare for training sessions | Approximate input(days) needed to manage training sessions | Approximate input(hours) needed to manage training sessions | Input(days) needed to administrate training sessions | Input(hours) needed to administrate training sessions | BAS Training Sessions scheduled for 2019/20 | Duration (Days) | Input(hours) needed to conduct training sessions | Approximate input(days) needed to prepare for training sessions | Approximate input(days) needed to manage and administrate training sessions | Approximate input(hours) needed to manage and administrate training sessions | E-mails send to invite users to attend training |  | 30 | 30
| General Principles | 3 | 24 | 16 | 3.3125 | 26.5 | 2.5 | 20 | General Principles | 3 | 24 | 16 | 4.8125 | 38.5 | Consolidate nominations received |  | 960 | 960
BAS currently has 8 training modules, Sundry Payments and Purchase Orders are no longer part of the training provided since the implementation of LOGIS. System Controller training are provided by National Treasury as and when needed, due the fact that the system controller functions is performed at the BAS Support and Administration unit. | General Journals | 2 | 16 | 16 | 3.3125 | 26.5 | 2.5 | 20 | General Journals | 2 | 16 | 16 | 4.8125 | 38.5 | Send e-mails to confirm training sessions (can be one email or an email per department) |  | 120 | 120
| Financial Reporting | 2 | 16 | 16 | 3.3125 | 26.5 | 2.5 | 20 | Financial Reporting | 2 | 16 | 16 | 4.8125 | 38.5 | Prepare training material | 240 | 240 | 240
| Bank Reconciliation | 3 | 24 | 16 | 3.3125 | 26.5 | 2.5 | 20 | Bank Reconciliation | 3 | 24 | 16 | 4.8125 | 38.5 | Facilitate logistical arrangements for training session | 120 |  | 120
| SAL/Persal Exceptions | 3 | 24 | 16 | 3.3125 | 26.5 | 2.5 | 20 | SAL/Persal Exceptions | 3 | 24 | 16 | 4.8125 | 38.5 | Mark Exam papers |  | 240
| Cash Receipts | 5 | 40 | 16 | 3.3125 | 26.5 | 2.5 | 20 | Cash Receipts | 5 | 40 | 16 | 4.8125 | 38.5 | Update the training database (Training venue accommodate 17 people, hence updates are based on 17 trainees per session) | 360 |  | 360
| Debt | 5 | 40 | 16 | 3.3125 | 26.5 | 2.5 | 20 | Debt | 5 | 40 | 16 | 4.8125 | 38.5 | Prepare, print and distribute certificates | 480 |  | 480
| Budgets | 2 | 16 | 16 | 3.3125 | 26.5 | 2.5 | 20 | Budgets | 2 | 16 | 16 | 4.8125 | 38.5 | Average minutes to arrange and finalise a training session | 1200 | 1590 | 2310
| As per training schedule | 5 | 40 | 16 | 3.3125 | 26.5 | 2.5 | 20 | As per training schedule | 5 | 40 | 16 | 4.8125 | 38.5 | Average hours to arrange and finalise a training session | 20 | 26.5 | 38.5
| As per training schedule | 5 | 40 | 16 | 3.3125 | 26.5 | 2.5 | 20 | As per training schedule | 5 | 40 | 16 | 4.8125 | 38.5 | Average days to arrange and finalise a training session | 2.5 | 3.3125 | 4.8125
| Adhoc | 3 | 24 | 16 | 3.3125 | 26.5 | 2.5 | 20 | Adhoc | 3 | 24 | 16 | 4.8125 | 38.5
| Adhoc | 3 | 24 | 16 | 3.3125 | 26.5 | 2.5 | 20 | Adhoc | 3 | 24 | 16 | 4.8125 | 38.5
| Adhoc | 5 | 40 | 16 | 3.3125 | 26.5 | 2.5 | 20 | Adhoc | 5 | 40 | 16 | 4.8125 | 38.5
| Total hours per financial year | 46 | 368 | 208 | 43.0625 | 344.5 | 32.5 | 260 | Total hours per financial year | 46 | 368 | 208 | 62.5625 | 500.5
| 16 LOGIS Training sessions to be held per Financial Year as per the APP | [7 empty] | 16 LOGIS Training sessions to be held per Financial Year as per the APP
Approximate input needed to prepare, conduct and finalise training sessions. | LOGIS Training Sessions | Duration (Days) | Approximate input(hours) needed to conduct training sessions | Approximate input(days) needed to prepare for training sessions | Approximate input(days) needed to manage training sessions | Approximate input(hours) needed to manage training sessions | Approximate input(days) needed to administrate training sessions | Approximate input(hours) needed to administrate training sessions | LOGIS Training Sessions scheduled for 2019/20 | Duration (Days) | Approximate input(hours) needed to conduct training sessions | Approximate input(days) needed to prepare for training sessions | Approximate input(days) needed to manage and administrate training sessions | Approximate input(hours) needed to manage and administrate training sessions
| Logis Literacy | 3 | 24 | 16 | 3.3125 | 26.5 | 2.5 | 20 | Logis Literacy | 3 | 24 | 16 | 4.8125 | 38.5
| Logis Literacy | 3 | 24 | 16 | 3.3125 | 26.5 | 2.5 | 20 | Logis Literacy | 3 | 24 | 16 | 4.8125 | 38.5
| Logis Posted/Automated Transit Manual | 5 | 40 | 16 | 3.3125 | 26.5 | 2.5 | 20 | Logis Posted/Automated Transit Manual | 5 | 40 | 16 | 4.8125 | 38.5
| Logis Order | 5 | 40 | 16 | 3.3125 | 26.5 | 2.5 | 20 | Logis Order | 5 | 40 | 16 | 4.8125 | 38.5
| Logis Payments | 5 | 40 | 16 | 3.3125 | 26.5 | 2.5 | 20 | Logis Payments | 5 | 40 | 16 | 4.8125 | 38.5
| Logis Asset Miscellaneous | 5 | 40 | 16 | 3.3125 | 26.5 | 2.5 | 20 | Logis Asset Miscellaneous | 5 | 40 | 16 | 4.8125 | 38.5
| Logis Literacy | 3 | 24 | 16 | 3.3125 | 26.5 | 2.5 | 20 | Logis Literacy | 3 | 24 | 16 | 4.8125 | 38.5
| Logis Asset Verification | 5 | 40 | 16 | 3.3125 | 26.5 | 2.5 | 20 | Logis Asset Verification | 5 | 40 | 16 | 4.8125 | 38.5
| Logis System Controller Admin | 5 | 40 | 16 | 3.3125 | 26.5 | 2.5 | 20 | Logis System Controller Admin | 5 | 40 | 16 | 4.8125 | 38.5
| Logis Asset Management | 5 | 40 | 16 | 3.3125 | 26.5 | 2.5 | 20 | Logis Asset Management | 5 | 40 | 16 | 4.8125 | 38.5
| Logis Posted/Automated Transit Manual | 5 | 40 | 16 | 3.3125 | 26.5 | 2.5 | 20 | Logis Posted/Automated Transit Manual | 5 | 40 | 16 | 4.8125 | 38.5
| Logis Literacy | 3 | 24 | 16 | 3.3125 | 26.5 | 2.5 | 20 | Logis Literacy | 3 | 24 | 16 | 4.8125 | 38.5
| Logis Payments | 5 | 40 | 16 | 3.3125 | 26.5 | 2.5 | 20 | Logis Payments | 5 | 40 | 16 | 4.8125 | 38.5
| Logis System Controller Functional | 10 | 80 | 16 | 3.3125 | 26.5 | 2.5 | 20 | Logis System Controller Functional | 10 | 80 | 16 | 4.8125 | 38.5
| Logis Literacy | 3 | 24 | 16 | 3.3125 | 26.5 | 2.5 | 20 | Logis Literacy | 3 | 24 | 16 | 4.8125 | 38.5
| As per training scheduled | 10 | 80 | 16 | 3.3125 | 26.5 | 2.5 | 20 | As per training scheduled | 10 | 80 | 16 | 4.8125 | 38.5
| Adhoc | 5 | 40 | 16 | 3.3125 | 26.5 | 2.5 | 20 | Adhoc | 5 | 40 | 16 | 4.8125 | 38.5
| Total hours per financial year | 85 | 680 | 272 | 56.3125 | 450.5 | 42.5 | 340 | Total hours per financial year | 85 | 680 | 272 | 81.8125 | 654.5
| Process: The Deputy Director send the training programme in March/April to all the Logis System controllers, BAS sub-system controllers and/or representatives to requests nominations. Nominations received are then consolidated by the Assistant Director as per the training session he/she will conduct. These nominations are then captured on the training database. The trainer will then send an email 1 to 2 weeks before the training to confirm attendance for the nominated officials or update the training database as per the changes requested by departments. The trainer then need to print the learning material, attendance register, evaluation sheets, exam papers, conduct the training, mark the exam papers, update the training database, prepare and print the certificates, cover letters, and have the certificates signed. Certificates are usually handed out at the Provincial user forums unless otherwise requested. The days/hours above is in consideration of all the preparations and finalisations. | [7 empty] | Process: The Deputy Director send the training programme in March/April to all the Logis System controllers, BAS sub-system controllers and/or representatives to requests nominations. Nominations received are then consolidated by the Financial Administration Officer. These nominations are then captured on the training database. The FAO will then send an email 1 to 2 weeks before the training to confirm attendance for the nominated officials or update the training database as per the changes requested by departments. The FAO will then prepare and print the attendance register and evaluation sheets. The trainer then need to print the learning material, exam papers, conduct the training, and mark the exam papers. The FAO will then update the training database, prepare and print the certificates, cover letters, and have the certificates signed. Certificates are usually handed out at the Provincial user forums unless otherwise requested. The days/hours above is in consideration of all the preparations and finalisations.
| FY 2019/2020 | FY 2019/2020 | FY 2020/2021 |  | FY 2019/2020 (Hours)/ 5xAD's | FY 2020/2021 (Hours)/ 5xAD's | FY 2019/2020 (Hours)/ 1xAD | FY 2020/2021 (Hours)/ 1xAD | FY 2019/2020 (Hours)/ 1xFAO | FY 2020/21 (Hours)/ 1xFAO
| Working days per FY cycle | 252 | 250 |  | 10080 | 10000 | 2016 | 2000 | 2016 | 2000
| Weekends | 104 | 104
| Public Holidays | 12 | 12
| Remaining hours - scenario 1 |  |  |  | 9032 | 8952 | 1221 | 1205 | 1416 | 1400
| Remaining hours - scenario 2 |  |  |  | 9032 | 8952 | 0 | 0 | 861 | 845
| BAS - National user group forums | Time away from office/working hours | LOGIS - National user group forums | Time away from office/working hours
| February | 12 | Feb/March | 12
| May | 20 | May/June | 12
| August | 12 | August/September | 12
| November | 20 | November/December | 12
|  | 64 |  | 48
| BAS - Provincial user group forums | Max. Average hours | LOGIS - Provincial user group forums | Max. Average hours
| Feb/March | 5 | Feb/March | 5
| May/June | 5 | May/June | 5
| August/September | 5 | August/September | 5
| November/December | 5 | November/December | 5
|  | 20 |  | 20
FY 2019/2020 | Assumption | Scenario 1: Conduct training (5 AD's) | Scenario 1: Management of training (1 AD) | Scenario 1: Administration of training (1 FAO) | Scenario 2: Conduct training (5 AD's) | Scenario 2: Management and Administration of training (1 FAO)
| Average working hours p/a | 10080 | 2016 | 2016 | 10080 | 2016
| Hours spend on training | 1528 | 795 | 600 | 1528 | 1155
| BAS user forums | 84 | 84 | 84 | 84 | 84
| LOGIS user forums | 68 | 68 | 68 | 68 | 68
| Average hours left after training/workshops | 8400 | 1069 | 1264 | 8400 | 709
| Average hours spend on training per official | 305.6 | 795 | 600 | 305.6 | 1155
| Working Days required per official for capacity building | 38.2 | 99.375 |  | 38.2 | 144.375
FY 2020/2021 | Assumption | Scenario 1: Conduct training (5 AD's) | Scenario 1: Management of training (1 AD) |  | Scenario 1: Administration of training (1 FAO) | Scenario 2: Conduct training (5 AD's) | Scenario 2: Management and Administration of training (1 FAO)
| Average working hours p/a | 10000 | 2000 |  | 2000 | 10000 | 2000
| Training | 1048 | 795 |  | 600 | 1048 | 1155
| BAS user forums | 84 | 84 |  | 84 | 84 | 84
| LOGIS user forums | 0 | 0 |  | 0 | 0 | 0
| Average hours left after training/workshops | 8868 | 1121 |  | 1316 | 8868 | 761
| Average hours spend on training per Official | 209.6 | 795 |  | 600 | 209.6 | 1155
| Average days spend on training per Official | 26.2 | 99.375 |  | 75 | 26.2 | 144.375
Note on C65: SMaclean: Extra day included for SCOA forums - held twice a year or as the need arise
Note on C67: SMaclean: Extra day included for SCOA forums - held twice a year or as the need arise

## Monitoring and Support
BAS and LOGIS Calls logged and resolved for MTEF 2016/17 - 2018/19
Minutes
[18 empty] | Requests | Incidents
[18 empty] | 15 | 240
[5 empty] | YoY Increase/decrease | [5 empty] | YoY Increase/decrease |  | Average time allocated to calls in minutes |  |  |  | Average time spend on calls in minutes |  |  | Average time spend on Supplier Admin and Codification
| BAS CALLS | 2016/17 | 2017/18 | 2018/19 | 2017/18 | 2018/19 | LOGIS CALLS | 2016/17 | 2017/18 | 2018/19 | 2017/18 | 2018/19 |  | 2016/2017 | 2017/2018 | 2018/2019 | 2016/2017 | 2017/2018 | 2018/2019 | MTEF 2016/2017 - 2018/2019 | Average time spend per year
| Total calls | 1649 | 1609 | 625 | -2.426% | -61.16% | Total calls | 4560 | 1288 | 303 | -71.75% | -76.48% | Requests | 4863 | 2475 | 773 | 72945 | 37125 | 11595 | 872 | 290.6667
| Resets | 895 | 815 | 103 | -8.939% | -87.36% | New ICN's | 1054 | 711 | 277 | -32.54% | -61.04% | Incidents | 1346 | 422 | 37 | 323040 | 101280 | 8880
[7 empty] | Supplier Admin | 1350 | 84 | 12 | -93.78% | -85.71% | Total | 6209 | 2897 | 810 | 63.776 | 47.7753 | 25.2778
| Average per quarter | 412.25 | 402.25 | 156.25 |  |  | Average per quarter | 1140 | 322 | 75.75 |  |  | Average minutes spend on calls |  |  |  | 45.6097 |  |  | 290.6667
| Average per Official/per quarter | 103.0625 | 100.5625 | 39.0625 |  |  | Average per Official/per quarter | 142.5 | 40.25 | 12.625
| Average Hours spend per FY to resolve calls | 1253.506 | 1223.0995 | 475.1008 |  |  | Average Hours spend per FY to resolve calls | 3466.3355 | 979.0877 | 230.3289
| Average Hours spend for MTEF 2016/17-2018/19 to resolve calls | 2951.7063 |  |  |  |  | Average Hours spend for MTEF 2016/17-2018/19 to resolve calls | 4675.7521
| Average Hours spend per official to resolve calls for MTEF 2016/17-2018/19 | 983.9021 |  |  |  |  | Average Hours spend for MTEF 2016/17-2018/19 to resolve calls per AD (3), 4FAO's for 2 FY's - Average 3 | 1558.584
[7 empty] | Percentage of ICN and Supplier Administrations calls processed by FAO | 56.71% | 883.8142 | 674.7698
| Monitoring and Support services rendered to 13 Departments and 47 Logis stores | [5 empty] | Average hours it might take to finalise quarterly security verifications per department for BAS and LOGIS | [5 empty] | Average per FY
| Departments | 2017/2018 | 2016/2017 | BAS USERS | LOGIS USERS | Users with BAS and LOGIS User-ids | Request and download reports | Filter data for information as per the security verifications requests | Verify documents against reports | Update the Matrix | Prepare Security Verification for the department | Visit the department to verify users and have the security verification signed off by the CFO | Average time allocated to Security Verifications per department on both systems
1 | NC: Agriculture, Land, Reform & Rural Reform | 68 | 60 | 39 | 35 | 13 | 4 | 2 | 2 | 2 | 2 | 20 | 128
1 | NC: Environment & Nature Conservation | 40 | 46 | 26 | 17 | 15 | 4 | 2 | 2 | 2 | 2 | 20 | 128
1 | NC: Roads & Public Works | 94 | 50 | 45 | 60 | 22 | 4 | 2 | 2 | 2 | 2 | 20 | 128
2 | NC: Provincial Treasury | 32 | 51 | 27 | 27 | 16 | 4 | 2 | 2 | 2 | 2 | 20 | 128
2 | NC: Social Development | 141 | 73 | 80 | 80 | 54 | 4 | 2 | 2 | 2 | 2 | 20 | 128
3 | NC: Health | 147 | 167 | 146 | 244 | 77 | 4 | 2 | 2 | 2 | 2 | 20 | 128
3 | NC: Office of the Premier | 27 | 31 | 24 | 13 | 10 | 4 | 2 | 2 | 2 | 2 | 20 | 128
4 | NC: Transport, Safety & Liaison | 59 | 52 | 39 | 17 |  | 4 | 2 | 2 | 2 | 2 | 20 | 128
4 | NC Economic Development | 36 | 57 | 35 | 20 | 20 | 4 | 2 | 2 | 2 | 2 | 20 | 128
4 | NC: Sport, Arts & Culture | 59 | 42 | 33 | 23 | 14 | 4 | 2 | 2 | 2 | 2 | 20 | 128
5 | NC: Education | 73 | 69 | 52 | 73 | 32 | 4 | 2 | 2 | 2 | 2 | 20 | 128
5 | NC:CO-OP Gov, Human Settlements and Traditional Affairs | 54 | 72 | 56 | 51 | 36 | 4 | 2 | 2 | 2 | 2 | 20 | 128
| TOTAL USERS | 830 | 770 | 602 | 660 | 309 | Total hours needed per FY to perform security verifications per department per system | [5 empty] | 1536
Time allocated as such to make provision for departments like Health who has more than the average number of users, and therefore more activities. Reports take longer to download because of the size of the report (can be anything from 900 to 2000 pages). The average time for departments like OTP will be much less than the allocated time above (reports for smaller departments can be from 100 - 300 pages. The size of the reports depends on the number of transactions/activities per month.
| Current BAS users per Syscon | 200.6667
| Current LOGIS users per Syscon | 330
| Average users per Syscon | 190.6
| Average hours needed per official to perform Security verifications on Bas and LOGIS respectively | 1536
Note on S4: SMaclean: Maximum time it will take to resolve a request is between 5 and 15 minutes. Incidents take longer to resolve, however most incidents that cannot be resolved within approximately 3 hours are referred to National Treasury.
Note on N9: SMaclean: A request can be done within 2 - 15 minutes, i.e. resets, user creations, Add supplier, Create an ICN, Segments, Capture a Parameter, Amend a user profile, activate a segment detail e.g. Item. This is the standard time in which requests can be finalised - under normal circumstances (not taking into account system problems) ALL calls must be resolved within 24 hours (3 Working days). This is not an indication of the time it takes to 'resolve' a call, but rather the time granted to attend to a call.
Note on B10: SMaclean: Special reference made to resets as the function has been automated in 2017
Note on H10: SMaclean: Special reference to Item control number - ICN's has significantly decreased as Implementation for the Province are done, except for the New Hospital in De Aar.
Note on N10: SMaclean: Incidents range from 5 minutes to more than 3 days if the call was referred to National Treasury. Incidents include request for information, reports on old databases. Incidents that cannot be resolved within approximately 4 hours (not consecutive hours), are referred to National Treasury, hence the maximum time allocated for purposes of this PER is 4 hours.
Note on H11: SMaclean: Special reference to requests from suppliers, the implementation of CSD has lead to a significant decrease in request
Note on K13: SMaclean: Calls divided by an average of 5 officials, 1 resigned as at 01 June 2018, 1 transferred as at 01 October 2018, 1 resigned as at end of November 2018
Note on B40: SMaclean: Users per Syscon if BAS and LOGIS are merged.

## Process flows
Similarities/Differences between BAS and LOGIS in terms of roles of Deputy Directors and Assistant Directors (BAS had not appointed and Administrative officer in the past 10 years)
|  | The co-ordination, implementation and maintenance process of BAS and LOGIS for departments (system controllers). |  | Additional Notes |  | The co-ordination, implementation and maintenance process of BAS and LOGIS for departments (Deputy Directors). |  | Additional Notes
|  | BAS | LOGIS |  |  | BAS | LOGIS
| 1 | Similarities |  |  | 1 | Similarities
| 1.1 | A checklist to list all the critical actions that must take place to ensure the successful implementation of the BAS system | A checklist to list all the critical actions that must take place to ensure the successful implementation of the LOGIS system | All Procurement Integration (PI) users need to be captured on BAS as well with user level PI, for PI interfaces to take place between BAS and LOGIS. | 1.1 | Manage and/or coordinate the capacity building of all BAS users - overall managerial responsibility for BAS training in the province, represent the province at National BAS user forums/workshops, responsible for Provincial user forums | Manage and/or coordinate the capacity building of all LOGIS users - overall managerial responsibility for LOGIS training in the province, represent the province at National LOGIS user forums/workshops, responsible for Provincial user forums
| 1.2 | Create preparation and implementation plans and obtain signoff – usually signed off by the CFO | Create preparation and implementation plans and obtain signoff – usually signed off by the CFO |  | 1.2 | Manage the component - perform strategic and operation planning, manage stakeholder relationships, oversee the administrative support functions, perform people, financial asset management | Manage the component - perform strategic and operation planning, manage stakeholder relationships, oversee the administrative support functions, perform people, financial asset management
| 1.3 | Asses the technical environment in the departments and align as per the need of the system | Asses the technical environment in the departments and align as per the need of the system |  | 1.3 | Monitor quarterly security checks, amend and implement amendments of the provincial BAS Security Management Manual. | Monitor quarterly security checks, amend and implement amendments of the provincial BAS Security Management Manual.
| 1.4 | Compile a Provincial policy/procedure manual regarding the utilisation of User-id’s | Compile a Provincial policy/procedure manual regarding the utilisation of User-id’s |  | 1.4 | Monitor and report on the BAS vs LOGIS utilisation | Monitor and report on the BAS vs LOGIS utilisation
| 1.5 | Create BAS users, set up security profiles, grant users access to workflows as per their job descriptions and add printers. | Create LOGIS users, set up security profiles, grant users access to workflows as per their job descriptions and add printers |  | 2 | Differences
| 1.6 | Monitor compliance and enforcement of prescribed legislation, policies and guidelines relating to BAS processes, render a support service to all provincial BAS users, building capacity of BAS users | Monitor and verify the utilisation of LOGIS and LBIS at the current live sites, Co-ordinate LOGIS support services and provide guidance to the current live sites, Co-ordinate the capacity building of LOGIS users |  | 2.1 | Manage the support services and guidance rendered to Provincial BAS users, Provide Financial year-end guidance- adherence to prescribed Month, Year and Final Audit closure, Ensure segment changes as per the budget statement are effected on BAS and submit to PERSAL to capture changes, i.e. Objective and Responsibility changes. | Manage the preparation, implementation and maintenance of LOGIS at sites in the province
| 1.7 | Compile, prepare and maintain BAS guidelines and training materials. Conduct training needs analysis and provide BAS training services accordingly. Update and maintain the training database. Attend National user forums and coordinate Provincial user forums | Compile, prepare and maintain LOGIS guidelines and training materials. Conduct training needs analysis and provide LOGIS training services accordingly. Update and maintain the training database. Attend National user forums and coordinate Provincial user forums | Current scenario: BAS system controllers- 3 Assistant Directors, conducting training for BAS and 1 Assistant Director at LOGIS conducting training for LOGIS. |  | Provide Financial year-end guidance- adherence to prescribed Month, Year and Final Audit closure | Assess self-accountable sites that are identified to be implemented on LOGIS, overall managerial responsibility for the preparation, implementation and activation of sites | LOGIS has been implemented successfully across the Province.
| 2 | Differences |  |  |  | Ensure segment changes as per the budget statement are effected on BAS and submit to PERSAL to capture changes, i.e. Objective and Responsibility changes | Present and introduce management reports and other LOGIS related facilities to manage activated sites, consolidate and submit rollout progress reports
| 2.1 | Capture Responsibilities, Projects, Regional Identifiers, Assets, and Objectives. Activate/Re-instate Items, Infrastructure and Fund | Determine if the department has an Asset/stock catalogue, if consumption history is available and if the list of allocated assets is updated. All Assets/Stock need to be added on LOGIS | The code structure are captured and maintained on BAS, whereas Assets, Inventories and Consumables are captured and maintained on LOGIS |  | Rendering a Provincial BAS helpdesk function to all BAS users and assist with the implementation of a change in Provincial Banker as and when needed. | Monitor functional support on LOGIS, Supplier Administration and the Codification process. | Supplier administration has significantly decreased as a result of the implementation of CSD (Central Supplier Database)
| 2.2 | Capture Parameters, this include capturing the LOGIS stores created on LOGIS for PI purposes, | Create LOGIS stores for all departments | LOGIS create stores, whereas BAS create offices. The LOGIS stores still need to be captured under Parameter 187 - Regional Indicator, for PI to take place. | 2.2 | Manage the monitoring of compliance and enforcement of prescribed legislation, policies and guidelines relating to all BAS processes | Manage the monitoring of compliance to prescribed legislation, policies and guidelines relating to all BAS processes
| 2.3 | Capture and/or re-instate Transaction Processing Rules | Capture Item Control Numbers, Add Suppliers and Add Personnel. |  |  | Consolidate FYE closure dates and statuses, and report on the clearing of suspense accounts, examine, consolidate and report on the passing of Opening Journals | Download and analyse reports, point out shortcomings to sites, prepare LOGIS management information reports in terms of spend analysis, commitments and accruals, inventory reforms.
| 2.4 | Assist departments during Financial Month and Year - end closure to clear accounts - Debt Accounts, Receipts, Exceptions (BAS/PERSAL), Payables (BAS/LOGIS), monitor the capturing of Opening Journals and Budgets and assist with/monitor Final Audit Closure. | Monitor the loading of store item balances, oversee verification of assets/store items, update store control files. Verify content of monthly reports published on LBIS, point out shortcomings and advise departments accordingly, verify supplier administration, verify codification, visit self-accountable sites and perform Quality Assessments. |  | 3 | Challenges
| 3 | Challenges |  |  |  | To appoint a Deputy Director who can manage and oversee both systems, the official need to know the processes and procedures for both systems, need to have a thorough understanding of the operations of both systems, should be able to compile monthly reports for departments with regard to compliance and performance of both systems, point out shortcoming and provide assistance and support to departments.
| 3.1 | BAS and LOGIS System controllers need to be trained on both systems respectively
| 3.2 | Challenges in terms of 1.7, both LOGIS and BAS system controllers need to be trained on the LOGIS train-the-trainer course to be accredited to provide LOGIS training (only 1 AD in the LOGIS unit has attended this course). This is a six week course that is compulsory to be provided access to the LOGIS training database. BAS System controllers need training on the LOGIS system i.e. LOGIS Literacy and LOGIS System Controller Functional course, 2 of the 3 System controllers has attended and passed the LOGIS Literacy course, 1 still need to attend, 3 need to attend the 2 week system controller course. LOGIS System controllers need to attend all BAS courses (all of which are conducted Provincialy, except the system controller course). The reason for attending all BAS modules: the system controller course for BAS only focus on the system controller functions and not on the functionalities of BAS, i.e. Debts, Receipts, Bank Reconciliation, PERSAL Exceptions, General Journals, Financial Reporting, Budgets etc., whereas the LOGIS system controller course focus on the system controller functions as well as the Procurement and Assets processes.
| 3.3 | Challenges in terms of 2, LOGIS and BAS system controllers need to learn the processes and procedures for the respective systems. This challenge will mostly be dealt with by providing training, however some technical problems will require on the job training. This can only be dealt with by teaching and assisting each other as and when these challenges arise.

## Structure
BLUE - Changes to structure
Gold - Vacancies
GREEN - Proposed changes
[5 empty] | SCENARIO 1 |  | SCENARIO 2
| CURRENT STRUCTURE |  | PROPOSED STRUCTURE |  | COSTED PLAN STRUCTURE |  | COSTED PLAN STRUCTURE
| Directorate: Supporting and Interlinked Financial Systems |  | Directorate: Financial Information Management Systems (FIMS) |  | Directorate: Financial Information Management Systems (FIMS) |  | Directorate: Financial Information Management Systems (FIMS)
| Strategic Objective | To provide oversight and management of interlinked financial systems and enhancing compliance with the PFMA and other relevant legislation within the provincial administration | Purpose | To manage the provision of financial systems oversight for provincial government | Purpose | To manage the provision of financial systems oversight for provincial government | Purpose | To manage the provision of financial systems oversight for provincial government
| 1 X Director |  | 1 X Director |  | 1 X Director |  | 1 X Director
| 1x Secretary |  | 1x Secretary |  | 1x Secretary |  | 1x Secretary
| Sub-Directorate: BAS Support and Administration | Sub-Directorate: LOGIS Management and Support | Sub-Directorate: BAS Support and Administration | Sub-Directorate: LOGIS Management and Support | Sub-Directorate: BAS and LOGIS Support, Management and Administration |  | Sub-Directorate: BAS and LOGIS Support, Management and Administration
| Purpose | Purpose | Purpose | Purpose | Purpose |  | Purpose
| To manage and render functional support to BAS users | To managed and render functional support to LOGIS users | To manage and render functional support to BAS users | To managed and render functional support to LOGIS users | To managed and render functional support to BAS and LOGIS users |  | To managed and render functional support to BAS and LOGIS users
| 1 x Deputy Director | 1 x Deputy Director | 1 x Deputy Directors | 1 x Deputy Directors | 1 x Deputy Directors |  | 1 x Deputy Directors
| 3 x Assistant Director | 3 x Assistant Director | 3 x Assistant Director | 4 x Assistant Director | 6 x Assistant Director |  | 5 x Assistant Director
|  | 4 x Financial Administration officers |  | 3 x Financial Administration officers | 1 x Financial Administration Officer |  | 1 Financial Administration Officer
| Key Performance areas (KPA's) |  |  |  | Key Performance areas (KPA's)
| Deputy Director: BAS Support and Administration | Deputy Director: LOGIS Management and Support |  |  | Deputy Director | Assistant Directors (5 AD's - BAS and LOGIS Management, Support and Administration) | Deputy Director | Assistant Directors (5 AD's - BAS and LOGIS Management, Support and Administration)
| Manage the support services and guidance rendered to Provincial BAS Users | Manage the preparation, implementation and maintenance of LOGIS at sites in the province |  |  | Manage the preparation, implementation and maintenance of LOGIS sites in the province | Render support services and provide guidance to all provincial BAS and LOGIS users | AS PER SCENARIO 1 | Render support services and provide guidance to all provincial BAS and LOGIS users
| Manage the monitoring of compliance and enforcement of prescribed legislation, policy and guidelines relating to all BAS processes | Manage the monitoring of compliance to prescribed legislation, policies and guidelines relating to the LOGIS processes |  |  | Manage the support services and guidance rendered to provincial BAS and LOGIS users | Co-ordinate, implement and maintain LOGIS at sites. |  | Co-ordinate, implement and maintain LOGIS at sites.
| Manage and/or coordinate the performing of BAS system controller functions | Manage the support services and guidelines rendered to LOGIS users |  |  | Manage the monitoring of compliance and enforcement of prescribed legislation, policies and guidelines relating to all BAS and LOGIS users | Monitor compliance and enforcement of prescribed legislation, policies and guidelines relating to all BAS and LOGIS processes |  | Monitor compliance and enforcement of prescribed legislation, policies and guidelines relating to all BAS and LOGIS processes
| Manage and/or coordinate the capacity building of all BAS users | Manage the capacity building of LOGIS users |  |  | Manage and/or coordinate the performing of BAS and LOGIS system controller functions | Perform BAS System controller functions and monitor and verify the utilisation of BAS and LOGIS |  | Perform BAS System controller functions and monitor and verify the utilisation of BAS and LOGIS
| Manage the components | Manage the components |  |  | Manage and/or coordinate the capacity building of all BAS and LOGIS users | Capacity building of all BAS and LOGIS users - conduct training to all BAS and LOGIS users |  | Capacity building of all BAS and LOGIS users - conduct training to all BAS and LOGIS users (will include some administrative functions)
[5 empty] | Manage the component | Administrative management of the section/Unit |  | Administrative management of the section/Unit
| Assistant Directors: BAS Support and Administration (3) | Assistant Directors: LOGIS Support (2)
| Render a support service to all provincial BAS users | Co-ordinate, implement and maintain LOGIS sites |  |  | Assistant Director: Administration and Support | Financial Administration Officer: BAS and LOGIS Support |  | Financial Administration Officer: BAS and LOGIS Support
| Monitoring of compliance and enforcement of prescribed legislation, policy and guidelines relating to all BAS processes | Monitor and verify the utilisation of LOGIS and LBIS at current live sites |  |  | Compile, prepare and maintain BAS and LOGIS training guidelines and materials | Facilitate logistics relating to training. |  | Compile, prepare and maintain training materials and guidelines and facilitate logistics relating to training.
| Perform BAS System controller functions | Co-ordinate LOGIS support services and provide guidance to the current live sites |  |  | Provide training administrative services for BAS and LOGIS | Prepare and distribute results/certificates to all users |  | Provide training administrative services for BAS and LOGIS, including the preparation, printing and distribution of certificates
| Building Capacity of BAS users | Co-ordinate the capacity building of LOGIS users |  |  | Manage the maintenance of the training database | Maintain the training database |  | Manage and maintain the training database
| Administrative management of Section/Unit | Administrative management of Section/Unit |  |  | Monitor/conduct LOGIS Supplier administration and codification functions | Perform LOGIS Supplier administration and codification functions |  | Perform LOGIS Supplier administration and codification functions
[5 empty] | Manage the coordination of BAS and LOGIS user forums | Co-ordinate BAS and LOGIS user forums |  | Co-ordinate BAS and LOGIS user forums
| Assistant Directors: LOGIS Training (1) | Administrative Officer: LOGIS Training (1) |  |  | Administrative management of the section/Unit | Provide guidance on LOGIS circulars, practice notes and LOGIS tables |  | Provide guidance on LOGIS circulars, practice notes and LOGIS tables
| Develop training materials | Conduct LOGIS training to all LOGIS users
| Provide/conduct LOGIS training to all LOGIS users | Provide inputs on the development and updating of training materials and manuals
| Co-ordinate user forums | Support Personnel and Salary controllers in the provincial departments with LOGIS related problems
| Administrative management of Section/Unit | Provide guidance on LOGIS circulars, practice notes and LOGIS tables
Facilitate logistics relating to training
| Assistant Directors: LOGIS Supplier Admin and Codification (2), 1 filled, 1 vacant | Administrative Officer: LOGIS Implementation and support (1)
| Conduct/monitor the verification and authorisation of banking details and supplier credentials | Prepare, implement and maintain LOGIS at sites
| Perform codification functions according to prescribed standards | Support the utilisation of LOGIS and LBIS by current live sites
| Provide LOGIS support with regards to supplier administration and codification | Render the LOGIS support services and guidance provided to the current live sites
Note on C21: SMaclean: 3 Vacancies as per current approved structure, 1 post is filled

## Graphs
BAS CALLS | 2016/17 | 2017/18 | 2018/19
Total calls | 1649 | 1609 | 625
Resets | 895 | 815 | 103
LOGIS CALLS | 2016/17 | 2017/18 | 2018/19
Total calls | 4560 | 1288 | 303
New ICN's | 1054 | 711 | 277
Supplier Admin | 1350 | 84 | 12
Row Labels | 2015/2016 | 2016/2017 | 2017/2018 | 2018/2019
BAS Support | 2125164.87 | 2149398.96 | 2305267.68 | 2445651.9
Basic Salary | 1856190.65 | 1848458.91 | 2002679.7 | 2150202.72
Housing Allowances | 50808 | 48108 | 60060 | 56069.94
NON PENSINABLE ALLOWANCES | 96258.72 | 104790.84 | 113609.28 | 121386.24
PERFOMANCE BONUS | 0 | 0
SERV BASED |  | 18582 | 0
SERVICE BONUS | 121907.5 | 100226.25 | 109155 | 117993
LOGIS Support | 3023860.12 | 3264281.27 | 3540885.95 | 3186111.12
Basic Salary | 2657931.77 | 2884453.32 | 3134762.19 | 2836642.43
Housing Allowances | 74400 | 82800 | 96804 | 69795.92
NON PENSONABLE ALLOWANCES | 84268.23 | 93835.17 | 103937.01 | 113310.72
PERFOMANCE BONUS | 27183.12 | 18082.95 | 0 | 0
SERV BASED | 0 | 0
SERVICE BONUS | 180077 | 185109.83 | 205382.75 | 166362.05
Grand Total | 5149024.99 | 5413680.23 | 5846153.63 | 5631763.02
Note on A6: SMaclean: Special reference made to resets as the function has been automated in 2017
Note on A23: SMaclean: Special reference to Item control number - ICN's has significantly decreased as Implementation for the Province are done, except for the New Hospital in De Aar.
Note on A24: SMaclean: Special reference to requests from suppliers, the implementation of CSD has lead to a significant decrease in request