## Logframe TRUE
Expenditure and Performance Review : School Infrastructure Delivery
LOGFRAME
A. Input |  | B. Activity |  | C. Output |  | Objectively Verifiable Indicators of Achievement | Means of Verification | Assumptions |  | D. Outcome |  | Objectively Verifiable Indicators of Achievement | Means of Verification | Assumptions |  | E. Goal |  | Objectively Verifiable Indicators of Achievement | Means of Verification | Assumptions
A-1 | Population demographics from STATSSA | B-1 | Prepare User Asset Management Plans | C-1 | Project Planning Data | Instrument 1 | IPMP / IRM | Reliable project data | TRUE | D-1 | Average annual improvement of 2% in space backlog | Instrument 4 | NEIMS / EFMS / Norms & Standards | Reliable & updated asset information | TRUE | E-1 | Improved school infrastructure | Instrument 7 | IPMP / IRM | Mature project team | TRUE
A-2 | Schools statistics from EMIS | B-3 | Prepare Procurement Strategy
A-3 | School infrastructure data from NEIMS | B-4 | Prepare Infrastructure Programme Management Plan
|  | B-5 | Obtain Implementation Authorisation | [6 empty] | D-1 | Average annual improvement of 2% in standard backlog | Instrument 5 | NEIMS / EFMS / Norms & Standards | Reliable & updated asset information | TRUE
|  | B-6 | Prepare Strategic Brief
|  | B-7 | Prepare Concept Design Report | C-2 | Project Implementation Data | Instrument 2 | IRM / BAS | Reliable project data | TRUE
|  | B-8 | Prepare Infrastructure Programme Implementation Plan | [6 empty] | D-1 | Average annual improvement of 2% in condition backlog | Instrument 6 | NEIMS / EFMS / Norms & Standards | Reliable & updated asset information | TRUE
|  | B-9 | Prepare Design Development Report
|  | B-10 | Prepare Production Information
|  | B-11 | Construct the Works
|  | B-13 | Issue Completion Certificate & compile Record Information
|  | B-15 | Accept Asset & update Asset Register and Accounting | C-3 | Asset Management Data | Instrument 3 | IRM / BAS / Asset Register | Reliable project data | TRUE
|  | B-18 | Mobilise User & Custodian Staff to manage the Asset
|  | B-19 | Mobilise Facilities Management Services
|  | B-20 | Manage Facility, Engineering Infrastructure & Property
|  | B-23 | Conduct Condition Assessment
|  | B-24 | Prepare Remaining Life-cycle Costing
|  | B-25 | Implement Preventitive Maintenance
|  | B-26 | Implement Breakdown Repairs
Prioritised project list with realistic budget allocations.
Clear description of project type.
Clear description project extent.
Alignment between IPMP values and IRM values.
Realistic cashflow per project.
Clear desciption of project type.
Clear description of project extent.
Alignment between IRM values of actual CAPEX and BAS values.
Informed split between Implementing Agent csot, PSP fees & Contractor cost.
Realistic cashflow per project.
Alignment between IRM actual MAINTENANCE values and BAS values.
Updated asset register with realistic asset accounting.
Measurable improvement based on updated information.
Alignment between NEIMS / EFMS data.
Measurable improvement based on updated information.
Alignment between NEIMS / EFMS data.
Measurable improvement based on updated information.
Alignment between NEIMS / EFMS data.
Clear goals.
Good project management information system.
Alignment between effort of team members

## Logframe FALSE
Expenditure and Performance Review : School Infrastructure Delivery
LOGFRAME
A. Input |  | B. Activity |  | C. Output |  | Objectively Verifiable Indicators of Achievement | Means of Verification | Assumptions |  | D. Outcome |  | Objectively Verifiable Indicators of Achievement | Means of Verification | Assumptions |  | E. Goal |  | Objectively Verifiable Indicators of Achievement | Means of Verification | Assumptions
A-1 | Population demographics from STATSSA | B-1 | Prepare User Asset Management Plans | C-1 | Project Planning Data | Instrument 1 | IPMP / IRM | Reliable project data | FALSE | D-1 | Average annual improvement of 2% in space backlog | Instrument 4 | NEIMS / EFMS / Norms & Standards | Reliable & updated asset information | FALSE | E-1 | Improved school infrastructure | Instrument 7 | IPMP / IRM | Mature project team | FALSE
A-2 | Schools statistics from EMIS | B-3 | Prepare Procurement Strategy
A-3 | School infrastructure data from NEIMS | B-4 | Prepare Infrastructure Programme Management Plan
|  | B-5 | Obtain Implementation Authorisation | [6 empty] | D-1 | Average annual improvement of 2% in standard backlog | Instrument 5 | NEIMS / EFMS / Norms & Standards | Reliable & updated asset information | FALSE
|  | B-6 | Prepare Strategic Brief
|  | B-7 | Prepare Concept Design Report | C-2 | Project Implementation Data | Instrument 2 | IRM / BAS | Reliable project data | FALSE
|  | B-8 | Prepare Infrastructure Programme Implementation Plan | [6 empty] | D-1 | Average annual improvement of 2% in condition backlog | Instrument 6 | NEIMS / EFMS / Norms & Standards | Reliable & updated asset information | FALSE
|  | B-9 | Prepare Design Development Report
|  | B-10 | Prepare Production Information
|  | B-11 | Construct the Works
|  | B-13 | Issue Completion Certificate & compile Record Information
|  | B-15 | Accept Asset & update Asset Register and Accounting | C-3 | Asset Management Data | Instrument 3 | IRM / BAS / Asset Register | Reliable project data | FALSE
|  | B-18 | Mobilise User & Custodian Staff to manage the Asset
|  | B-19 | Mobilise Facilities Management Services
|  | B-20 | Manage Facility, Engineering Infrastructure & Property
|  | B-23 | Conduct Condition Assessment
|  | B-24 | Prepare Remaining Life-cycle Costing
|  | B-25 | Implement Preventitive Maintenance
|  | B-26 | Implement Breakdown Repairs
Over-simplified (e.g. straight line) cashflow per project.
No / uncear desciption of project type.
No / unclear description of project extent.
Misalignment between IRM values of actual CAPEX and BAS values.
No / unrealistic split between Implementing Agent cost, PSP fees & Contractor cost.
Realistic cashflow per project.
Misalignment between IRM actual MAINTENANCE values and BAS values.
No / outdated asset register with unrealistic asset accounting.
Guessed improvement based on outdated information.
Misalignment between NEIMS / EFMS data.
Guessed improvement based on outdated information.
Misalignment between NEIMS / EFMS data.
Guessed improvement based on outdated information.
Misalignment between NEIMS / EFMS data.
No / unclear goals.
No / poor project management information system.
Misalignment between effort of team members
Project wish list.
Inconsistent budget allocations.
No / unclear description of project type.
No / unclear description project extent.
Alignment between IPMP values and IRM values.

## Config
TRUE
FALSE

## DBE Logframe
THE DEPARTMENT OF BASIC EDUCATION (DBE) LOGICAL FRAMEWORK TO IMPLEMENT THE IDMS IN THE EDUCATION SECTOR
IN TERMS OF THE TECHNICAL ASSISTANCE AGREEMENT BETWEEN DBE AND THE NATIONAL TREASURY.
Programme Description | Impact Indicators | Means of Verification/ Source | Assumptions
Goal: The overall Goal is for DBE to support the Government’s strategy to achieve socio-economic growth and development through improved infrastructure delivery in the Education Sector | 1. Effective policy, legislation and improved socio-economic growth. Baseline: The DBE is managing the DoRA grant for the construction and maintenance of new and replacement schools as well as the filling of key posts in the infrastructure units of Provincial Departments of Education. DBE is actively involved in the PICC processes. | • Education HEDCOM decisions; • PICC Secretariat reports. | The Government continues to support the implementation of the IDMS as the best practice methodology for infrastructure delivery.
| 2. IDMS capability (capacity and ability) to plan, manage, deliver and evaluate infrastructure delivery in the education sector. Baseline: Baseline provided in the Auditor General Infrastructure Performance Report for Education, 2011, the IDIP Strategic Review, 2013 and DBE and NT Reports on the Provincial Infrastructure Incentive Grant. | • AG Performance Reports; • IDMS Review Reports; • Provincial Infrastructure Incentive Grant Reports. | The Auditor General uses the IDMS as the basis for infrastructure delivery performance auditsducation HEDCOM decision.
| 3. Promoting the National Development Plan, 2030 in accordance with Chapter 9 and more specifically ensuring that the basic infrastructure requirements in schools are met. Baseline: DBE quarterly reports to the Presidency on its contribution to the NDP. | • DBE quarterly reports to the Presidency. | The IDMS is aligned to the NDP.
| 4. Outcome 1: Improvement of the Quality of Education, in accordance with the Presidency’s Measurable and Accountable Delivery System. Baseline: Reporting is currently on the provision of basic services (water, electricity and sanitation) in accordance with the Presidency’s requirements. | • DBE reports to the Presidency; • Presidency’s Reports on DBE performance in relation to Outcome 1.
| 5. Education Sector indicators and reporting in relation to infrastructure delivery and capacity. Baseline: DBE reports on infrastructure in the APP. | • DBE APPs. | Education Sector uses the norms and standards in the planning process, the norms and standards are costed and the budget is available to implement the norms and standards.
Purpose (Outcome) | Outcome Indicators | Means of Verification/ Source | Assumptions
In order to achieve the Goal the DBE will support the implementation of the Infrastructure Delivery Management System (IDMS) in the Education Sector at the national and provincial spheres of government. | 1. Education Sector compliance with the policy and legislative requirements in relation to infrastructure delivery management, especial in terms of the DoRA. Baseline: There is reporting on performance on Infrastructure Grants in accordance with the DoRA, but it requires improvement. Norms and Standards for schools infrastructure have been Gazetted but have not been costed. | • DBE Reports to NT on infrastructure delivery in DoRA; • DBE reports to HEDCOM and CEM on infrastructure delivery. | NT continues to engage DBE timeously on annual amendments to DoRA.
| 2. Formalised inter-governmental coordination in relation to the IDMS between the DBE and the Provincial Departments of Education. Baseline: The Education HEDCOM approved the IDMS and capacitation model for provincial infrastructure units however, monitoring of this decision can be improved. The DBE is rendering assistance to the provincial departments with the implementation of the IDMS | • HEDCOM decisions in relation to the IDMS; • DBE quarterly reports on provincial assistance.
| 3. Formalised intra-governmental cooperation and coordination between the National Treasury and the DBE to guide and oversee the implementation of the IDMS in the education sector. Baseline: (i) Approved provincial IDMS Framework Agreements. (ii) IDMS forum is not established in all provinces | • Provincial IDMS Framework Agreements; • DBE reports to NT on DoRA requirements. | NT will establish the intra-governmental IDMS structure at the national sphere of Government and will consult with DBE in this regard.
| 4. Capability of the Provincial Departments of Education to participate in the implementation of the Provincial IDMS’. Baseline: IDIP III provided a Technical Assistant to each Provincial Department of Education and organisation structure and competency profile has been developed and the filling of key posts are funded through DoRA. Not all posts are filled and not all appointees comply with the requirements in relation to qualifications and experience. | • Provincial Education reports on IDMS posts; • DBE reports to NT on DoRA requirements. | Provinces continue their support for the provincial IDMS Framework Agreements;
| 5. The Education Sector’s capacity to plan and manage infrastructure in accordance with IDMS requirements. Baseline: AG Performance Report for the Education Sector, 2011 as well as the DBE DoRA Capacitation Report to NT | • AG Performance Reports; • DBE capacitation report to NT. | The NT has a documented performance management system for the implementation of the Technical Assistance Agreement between DBE and NT.
| 6. Optimal use by the education sector of existing resources to achieve value for money. Baseline: In-year infrastructure spending patterns indicate increases towards the end of the financial year, fiscal dumping still occurring. Infrastructure prioritisation, planning and budgeting is only aligned to a limited extend. | • DBE quarterly reports on infrastructure spending in the sector; • DBE reports on the implementation of norms and standards. | • The IDMS is used to achieve value for money; • There are appropriate additional resources and tools to determine value for money at a project level.
| 7. Performance management of the implementation of IDMS at the programme level in relation to reporting, monitoring and evaluation. Baseline: DBE Quarterly Progress Reports to the IDIP PMU; IDIP PMU Quarterly and Annual progress reports; Quality Assurance Reports; TAs monthly reports, Review Reports (2009 and 2013). | • Documented programme level performance management system to be developed by NT. | The NT has a documented performance management system for the implementation of the Technical Assistance Agreement by the DBE.
Output 1 Proportional Contribution: 20 % | Key Performance Indicators | Means of Verification/ Source | Risks Risk Rating: Medium
The IDMS is institutionalised and sustainable in the Education Sector. | 1.1 The education sector is complying with the IDMS requirements in DoRA. Baseline: Most IDMS requirements are in DoRA, 2014 but compliance needs to improve and the DBE is managing the DoRA grant funding. Target: (i) Compliance with DoRA requirements in relation to the IDMS; (ii) Implementation of the Treasury Regulations which supports infrastructure planning and procurement once these Regulations have been published. | • DBE quarterly DoRA grant performance reports to NT. | The implications of ever changing DoRA requirements in terms of capacity, information and resources are not clearly considered and described by NT.
| 1.2 The Education HEDCOM oversees and monitors the implementation of the IDMS in the education sector. Baseline: HEDCOM approved the IDMS. Target: Effective planning and implementation of school infrastructure delivery by HEDCOM. | • HEDCOM reports on education infrastructure. | The Education HEDCOM does not focus on the IDMS per se but on infrastructure delivery in general terms.
| 1.3 DBE is an active member of the intra-governmental committee which is established by National Treasury to coordinate and monitor the implementation of the IDMS. Baseline: No formalised structure has been established by National Treasury and there is only ad hoc cooperation and limited intra-government coordination between DBE and NT in relation to the IDMS. Target: An IDMS structure is established at the national sphere of government and DBE is an active management member. | • Approved ToR of the structure: • Records of the establishment of the structure. | The NT does not establish an intra-government IDMS structure at the national sphere of government.
| 1.4 Provincial Departments of Education actively participate in the IDMS in accordance with the approved IDMS Framework Agreements. Baseline: IDMS was adopted by the Education HEDCOM whilst Provincial Framework Agreements were approved in 9 provinces but implementation are uneven amongst the 9 provinces Target: (i) IDMS institutionalisation in 9 Provinces and, (ii) compliance with relevant DoRA Sections, (iii) DBE encourages Provincial Education Departments to actively participate in the Provincial IDMS coordination structures. | • Education sector inputs to Provincial Framework Agreements; • Attendance registers of Provincial coordination meetings. | PTs does not fulfil their lead role in relation to the Provincial IDMS Agreements.
| 1.5 The IDMS body of knowledge is used by the education sector's infrastructure units for management, coordination and communication purposes. Baseline: Not fully operational. Target: 70% utilisation by the education sector of the electronic system which will be developed and implemented by NT. | • Education sector utilisation of IDMS web. | The NT is not successful in with the implementation of an IDMS web.
| 1.6 The Technical Assistance Agreement between DBE and National Treasury is implemented by the DBE. Baseline: The Agreement has been signed by the DG of DBE and the NT DDG: Intergovernmental Relations. Target: Implementation of the Agreement by the DBE in accordance with requirements in the Agreement (inclusive of this DBE Logical Framework). | • Signed Agreement and DBE Logframe; • DBE quarterly progress reports on the Technical Assistance Agreement; • DBE TA(s) monthly progress reports to the Programme Support Office (PSO); • PSO six monthly quality assurance reports to DBE and NT. | The NT does not provide clear planning, reporting, monitoring and evaluation methodologies in relation to the Technical Assistance Agreement.
Output 2 Proportional Contribution: 40% | Key Performance Indicators | Means of Verification/ Source | Risks Risk Rating: Medium
The Infrastructure Delivery Management (IDM) processes are operational and are being used by DBE and the Provincial Departments of Education to plan, implement and assess infrastructure delivery. | 2.1 Infrastructure portfolio planning in the education sector is improved. Baseline: (i) DBE/NT infrastructure planning assessment guideline, (ii) DBE and National Treasury assessment ratings of U-AMPs. Target: (i) Improved planning demonstrated in the User Asset Management Plans (U-AMP), (ii) education sector compliance with relevant sections in DoRA, (iii) the ratio of maintenance is improvement as a share of the budget. | • DBE/NT infrastructure planning assessment guideline; • Moderated education sector U-AMP Assessment Reports. | The IDM infrastructure planning methodology is too complex.
| 2.2 Improved infrastructure delivery strategies. Baseline: There is a NT/DBE guideline for analysing IPMPs and the analysis of IPMPs is done. Target: 100% of school infrastructure delivery projects delivered within the targeted periods aligned to the construction procurement strategy on the IPMP. . | • NT/DBE guideline for analysing IPMPs • Consolidated IPMP Analysis Reports; • DBE reports on DoRA compliance. | The information in the infrastructure plans is not fully aligned with the Education Sector targets.
| 2.3 Improved infrastructure implementation planning. Baseline: AG Report on Education Infrastructure Performance, 2011. Target: Improved quality of Project Execution Plans (PEPs). | • AG Performance Reports; • DBE’s annual consolidated report on the overall quality of PEPs
| 2.4 Compliance with the National Treasury’s Regulations and Standard Operating Procedures (SOPs) to support the IDMS. Baseline: Draft standards developed and published for public comments Target: Gazetted by the Minister of Finance and they are legal and the DBE and Education Sector complies with the requirements. | • Gazetted NT Regulations and SOPs; • NT status reports on education sector compliance. | There is resistance to the IDM based constructions reforms.
| 2.5 Support and participate in the development of the IDM Toolkit into an integrated IDMS body of knowledge. Baseline: DBE actively participated in the development and enhancement of the IDM Toolkit. Target: (i) DBE actively participates in the development and enhancement of the 2015 IDM Toolkit, (ii) DBE and the education sector participates in and contributes to the development of the IDMS body of knowledge. | • DBE inputs in relation to the IDM Toolkit enhancement; • ToR for the assignment; • Register of DBE attendance of the work sessions. | The various components of the IDMS are not aligned and integrated.
Output 3 Proportional Contribution: 30% | Key Performance Indicators | Means of Verification/ Source | Risks Risk Rating: Medium
There is appropriate professional capacity in the DBE and the Provincial Departments of Education to implement and sustain the IDMS. | 3.1 IDMS organisational structures and competence standards developed and implemented in the education sector. Baseline: (i) An education sector blueprint for Provincial Departments of Education were approved by the Education HEDCOM, (ii)153 professional posts were filled in the provincial Departments’ of Education Infrastructure Units by the end of September 2014. Target: (i) Competence standards developed and implemented in all the Provincial Departments of Education, (ii) the provincial posts on the approved establishment for infrastructure units comply with the defined competence requirements and, (iii) all the approved critical posts are filled in Provincial Departments’ of Education Infrastructure Units. | • DBE reports on DoRA; • Education sector approved competence standards; • DBE quarterly progress reports on the filling of key posts. | Provincial Departments of Education lack the ability to implement the IDMS capacitation.
| 3.2 The Education Sector participates in IDMS related training, research and development. Baseline: The Education Sector actively participated in the Infrastructure Delivery Management Programme (IDMP): Executive and Foundation Courses which have been developed and piloted in cooperation with the University of Pretoria. Target: (i) DBE participates in the enhancement of the courses and representatives of the education sector attend the courses, (ii) DBE lead with the development and implementation of induction courses for IDMS professionals in Provincial Departments of Education. | • DBE comments and inputs to NT on the IDMP; • Course selection of participants reports; • Course attendance registers; • Education sector induction course programme; • Attendance registers; • NT survey report on individual and organisation level impact. | The IDMP Executive and Foundation Courses have limited individual and organisational impact.
| 3.3 DBE and the Education Sector support and participate in knowledge sharing and lesson learning initiatives in relation to the IDMS. Baseline: DBE participated in the developed and implementation of the IDIP knowledge sharing system and in various IDMS specific knowledge sharing events at the national sphere of government. Target: (i) DBE continues its involvement in and support to IDMS knowledge management and, (ii) supports the establishment of Provincial Communities of Practice (CoPs), (iii) DBE and the education sector contributes to the IDMS body of knowledge (case studies, best practices and lessons learnt). | • COP agendas / minutes / reports / presentations / feedback if available; • Education sector lessons learned and case studies captured on the IDMS website. | Provincial COPs are not sustainable in the long term.
Output 4: Proportional Contribution: 10 % | Key Performance Indicators | Means of Verification/ Source | Risks Risk Rating: Medium
IDMS evaluation, monitoring and reporting systems are implemented and functional in the Education Sector. | 4.1 Effective results based reporting and monitoring on the implementation of the IDMS. Baseline: IRM, QA Reports, quarterly Education Sector progress reports to the IDIP PMU, Quarterly and Annual IDIP PMU Reports, IDIP Mid-term Review and Strategic Review. Target: (i) Self-assessment by DBE in accordance with the Accountable Technical Assistance Agreement (inclusive of this logical framework), (ii)Post-Inception Review, (iv) Medium Term Review (2016) and Strategic Review (2017), and (v) annual evaluation report on monitoring results, (vi) qualitative perceptions survey. | • DBE reports to NT on Technical assistance implementation; • Post-Inception Review Report; • Medium-term and Strategic Review Reports; • Annual evaluation report on monitoring results; • Six monthly qualitative perception survey reports. | • The monitoring, reporting and evaluation methodology for the Technical Assistance Agreement is not well defined and properly documented; • The information from the reports are not used by management to ensure sustainability of the IDMS.