## TITLE PAGE
ANNEXURE 1
ENFORCING ENFORCEMENT
By SUNITA BOODRAM
2019-12-23

## ANNEXURE 1 - Enforcement
IMPACT | IMP1 | A safer road network
Indicator |  | % reduction in road fatalities
Frequency |  | Annual
Source of data |  | Road Traffic Management Corporation Report
OUTCOME | OUTC1 | Reduction in road crashes and fatalities.
Indicator |  | Number of road fatalities
Frequency |  | Monthly
Source of data |  | Road Traffic Management Corporation Report
Final Output | FOUT1 | A monitored and patrolled road network.
Indicator |  | Kilometres of road network patrolled
Frequency |  | Daily
Source of data |  | Duty Rosters, Logsheets and OBs
Intermediate outputs | IOUT1 | Report on Findings on Legal and and Labour Implications | IOUT2 | Report on Baseline information. | IOUT3 | Costing Analysis Report | IOUT4 | Approved Implementation Plan | IOUT5 | Patrolled road network | IOUT6 | Evaluation Reports
Indicator | [9 empty] | Kilometres of road network patrolled
Frequency | [9 empty] | Daily
Source of data | [9 empty] | Duty Rosters, Logsheets and OBs
Activities | ACT 1.1 | Identify, analyse and determine legislative and labour implications | ACT 2.3 | Determine the current number of officers in KZN | ACT 3.4 | Determine feasibility of introducing a 3rd shift as opposed to continuing current overtime. | ACT 4.3 | Submit plan for approval | ACT 5.4 | Deploy officers with emphasis on hazardous locations | ACT 6.2 | Evaluate effectiveness of plan
Indicator |  |  |  | Number of traffic officers |  | Amount in Rs |  |  |  | Number of Officers |  | Performance reports
Frequency |  |  |  | Quarterly | [5 empty] | Daily |  | Quarterly
Source of data |  |  |  | PERSAL | [7 empty] | Road Traffic Management Corporation Report
Activities |  |  | ACT 2.2 | Identify hazardous locations | ACT 3.3 | Calculate the estimated number of new traffic officers that can be employed by dividing the average annual overtime costs by the average annual salary of one traffic officer | ACT 4.2 | Present Plan for Input and make amendments (If necessary) | ACT 5.3 | Developing work rosters | ACT 6.1 | Monitor incidence and number of road fatalities and hazardous locations
Indicator |  |  |  | Number of hazardous locations |  | Amount in Rs |  |  |  | Number of rosters |  | Performance reports
Frequency |  |  |  | Annual | [5 empty] | Daily |  | Quarterly
Source of data |  |  |  | Road Traffic Management Corporation Report | [7 empty] | Road Traffic Management Corporation Report
Activities |  |  | ACT 2.1 | Determine number of road fatalities in the past 4 years | ACT 3.2 | Establish current average annual overtime costs for traffic officers | ACT 4.1 | Prepare proposal and plan on preferred option | ACT 5.2 | Procuring of work resources (uniforms, vehicles, etc.)
Indicator |  |  |  | Number of road fatalities |  | Amount (in Rs) of overtime money paid to all traffic officers |  |  |  | Number of various equipment procured (Eg. Vehicles, guns, uniforms, radioes, pepper sprays, batons)
Frequency |  |  |  | Monthly |  | Monthly
Source of data |  |  |  | Road Traffic Management Corporation Departmental records |  | Overtime Claims PERSAL |  |  |  | SCM Reocrds
Activities |  |  |  |  | ACT 3.1 | Calculate average annual salary costs of a traffic officer |  |  | ACT 5.1 | Recruitment of new Pis
Indicator | [5 empty] | Amount (in Rs) of salary paid |  |  |  | Number of new Pis employed
Frequency | [5 empty] | Monthly
Source of data | [5 empty] | PERSAL |  |  |  | PERSAL
Activities
Indicator
Frequency
Source of data
Inputs |  | Legislation Collective Agreements |  | PERSAL Reports RTMC Reports Road Asset Management Plan Departmental road fatalities records |  | PERSAL Reports |  |  |  | Patrol vehicles Petrol Enforcement officers Arms Protective gear Uniforms Logbooks Roster Books Stationery Recruitment staff Procurement staff |  | Performance information reports Road crash statistics Fatality statistics
Performance indicator | [9 empty] | Kilometres of road network patrolled
Frequency | [9 empty] | Daily
Programme elements |  | Determine the Policy and legislative Environment |  | Analyse the Current Situation |  | Determine Cost Implications |  | Develop Implementation Plan |  | Undertake traffic enforcement |  | Monitor and Evaluate
Responsibility |  | Director : Policy and Planning (Programme 1) |  | Director : Policy and Planning (Programme 1) |  | Director : Policy and Planning (Programme 1) |  | Director : Policy and Planning (Programme 1) |  | CD : Traffic Management and Road Safety (Programme 4 - SubProgramme Traffic Enforcement) |  | Director : Monitoring and Evaluation Director : Road Traffic Inspectorate Director : Public Transport Enforcement Unit